## Worksheet
Date | Client Name | Campaign/Project | Objective | Key Activities | Performance Metrics | Progress Status | Next Steps | Owner
05/04/2024 | Acme Corp | Quarterly Sales Growth Campaign | Increase sales by 15% QoQ | Market research, email outreach, webinar hosting | Email open rate: 45%, Conversion rate: 8% | On track (80% completion) | Finalize campaign report by end of week | Sarah Thompson
05/07/2024 | BrightFlow Inc. | Product Launch - Version 3.0 | Achieve first 5,000 users in month one | Beta testing, PR outreach, social media launch | User sign-ups: 4,200 (94% of target) | On track | Begin post-launch support training | David Chen
05/10/2024 | NexGen Solutions | Enterprise Onboarding Program | Reduce onboarding time by 30% | Workflow automation, training modules, live coaching | Onboarding duration: 4.5 days (target: 6 days) | Ahead of schedule | Scale successful model to other clients | Lisa Park
05/14/2024 | GlobalTech Ltd. | Annual Customer Retention Review | Improve retention by 10% over current rate | Customer surveys, churn analysis, loyalty program roll-out | Retention rate: 86% (current: 76%) | Above target | Plan Q3 rewards initiative | James Reed