## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | 95% | Alex Johnson | On Track
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | 75% | Sarah Lee | On Track (Delayed by 2 days)
Design Phase | 2024-04-11 | 2024-05-05 | 35 | 60% | Marcus Brown | Delayed
Development Phase | 2024-05-06 | 2024-07-15 | 61 | 30% | Lena Patel | At Risk
Testing & QA | 2024-07-16 | 2024-08-31 | 46 | 15% | Tim Chen | Not Started
Deployment & Review | 2024-09-01 | 2024-09-30 | 30 | 0% | Jasmine Kim | <Not Started