## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
Project Initiation | 2024-01-15 | 2024-01-25 | 10 | Jane Smith | Completed | 100
Requirements Gathering | 2024-01-26 | 2024-02-15 | 20 | Mike Johnson | In Progress | 65
Design Phase | 2024-02-16 | 2024-03-15 | 30 | Sarah Lee | Not Started | 0
Development Phase | 2024-03-16 | 2024-05-15 | 60 | David Kim | In Progress | 40
Testing & Quality Assurance | 2024-05-16 | 2024-06-15 | 30 | Lisa Wong | Not Started | 0
Deployment & Training | 2024-06-16 | 2024-07-15 | 30 | Tom Reed | Not Started | 0
Post-Implementation Review | 2024-07-16 | 2024-07-31 | 15 | Jane Smith | Not Started | 0