## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%)
Project Planning | 2024-03-01 | 2024-03-15 | 15 | Completed | 100
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | In Progress | 70
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Not Started | 0
Development Phase | 2024-05-16 | 2024-07-31 | 76 | Not Started | 0
Testing & Quality Assurance | 2024-08-01 | 2024-09-15 | 55 | Not Started | 0
Deployment & Launch | 2024-09-16 | 2024-09-30 | 15 | Not Started | 0