## Worksheet
Task | Start Date | End Date | Duration | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | Completed
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 days | In Progress
Design Phase | 2024-02-16 | 2024-03-31 | 45 days | Planned
Development | 2024-04-01 | 2024-06-30 | 90 days | Not Started
Testing & QA | 2024-07-01 | 2024-08-15 | 45 days | Planned
Deployment | 2024-08-16 | 2024-08-31 | 15 days | Not Started
Post-Launch Review | 2024-09-01 | 2024-09-15 | 15 days | Planned