## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Person
Project Planning | 2024-03-01 | 2024-03-15 | 15 | On Track | John Doe
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | In Progress | Jane Smith
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Not Started | Mike Johnson
Development Phase | 2024-05-16 | 2024-07-31 | 87 | Planned | Sarah Lee
Testing & QA | 2024-08-01 | 2024-09-15 | 60 | Not Started | David Kim
Deployment & Launch | 2024-09-16 | 2024-10-31 | 46 | Not Started | Lisa Brown