## Worksheet
Task | Start Date | End Date | Status | Progress (%) | Owner | Duration (Days)
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | Completed | 100% | Jane Doe | 1
Requirements Gathering | 2024-03-16 | 2024-03-25 | In Progress | 75% | John Smith | 10
Design Phase (UI/UX) | 2024-03-26 | 2024-04-10 | Not Started | 0% | Alice Brown | 15
Development Phase | 2024-04-11 | 2024-05-30 | Not Started | 0% | Mike Lee | 51
Testing & QA | 2024-06-01 | 2024-06-20 | Not Started | 0% | Sarah Kim | 20
Final Review & Deployment | 2024-06-21 | 2024-06-30 | Not Started | 0% | David Wong | 10