## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%) | Dependencies | Milestones
P-001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Jane Doe | Completed | 100 | None | Yes
P-002 | Market Research Phase | 2024-03-16 | 2024-04-15 | 30 | John Smith | In Progress | 65 | P-001 | Yes
P-003 | Product Design Finalization | 2024-04-16 | 2024-05-10 | 35 | Alice Johnson | Not Started | 0 | P-002 | Yes
P-004 | Development Phase (Frontend) | 2024-05-11 | 2024-07-31 | 92 | Mike Brown | In Progress | 40 | P-003 | No
P-005 | Testing & QA Review | 2024-08-01 | 2024-08-31 | 31 | Sarah Lee | Not Started | 0 | P-004 | Yes
P-006 | Launch & Go Live | 2024-09-01 | 2024-09-30 | 30 | David Kim | Not Started | 0 | P-005 | Yes