## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%)
Project Kickoff | 2024-04-01 | 2024-04-05 | 5 | Completed | 100
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | In Progress | 75
UI/UX Design Phase | 2024-04-16 | 2024-05-10 | 25 | Not Started | 0
Development Phase (Frontend) | 2024-05-11 | 2024-06-30 | 60 | Not Started | 0
Testing & QA | 2024-07-01 | 2024-07-15 | 15 | Not Started | 0
Deployment & Launch | 2024-07-16 | 2024-07-25 | 10 | Not Started | 0