## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed | 100%
Market Research | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | In Progress | 65%
Product Design | 2024-04-11 | 2024-05-30 | 60 | Mike Chen | Planned | 0%
Development Phase | 2024-06-01 | 2024-08-15 | 95 | Alex Torres | Not Started | 0%
Testing & QA | 2024-08-16 | 2024-09-15 | 30 | Lisa Wong | Not Started | 0%
Launch Preparation | 2024-09-16 | 2024-10-31 | 46 | David Kim | Not Started | 0%
Post-Launch Review | 2024-11-01 | 2024-11-30 | 30 | Team Lead | Not Started | 0%