## Worksheet
Task | Start Date | End Date | Duration | Status | Progress (%) | Owner | Dependencies
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Completed | 100% | Manager A | None
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 days | In Progress | 60% | Team Lead B | Kickoff Meeting
Design Phase | 2024-03-16 | 2024-04-10 | 35 days | Planned | 0% | Designer C | Requirements Finalized
Development Phase | 2024-04-11 | 2024-06-30 | 81 days | Not Started | 0% | Dev Team D | Design Phase Complete
Testing & QA | 2024-07-01 | 2024-07-31 | 31 days | Delayed | 25% | QA Lead E | Development Complete
Deployment & Launch | 2024-08-01 | 2024-08-15 | 15 days | Scheduled | 0% | Manager A | Testing Complete