## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%) | Responsible Person
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Completed | 100% | Jane Doe
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 | In Progress | 75% | John Smith
Design Phase | 2024-02-16 | 2024-03-31 | 45 | Not Started | 0% | Lisa Brown
Development | 2024-04-01 | 2024-06-30 | 90 | Not Started | 0% | Mike Davis
Testing & QA | 2024-07-01 | 2024-08-15 | 45 | Not Started | 0% | Sarah Wilson
Deployment | 2024-08-16 | 2024-08-31 | 15 | Not Started | 0% | Tom Johnson