## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | On Track | John Doe
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | In Progress | Jane Smith
Design Phase | 2024-04-11 | 2024-05-31 | 61 | Not Started | Alex Brown
Development Phase | 2024-06-01 | 2024-08-31 | 90 | Planned | Mike Taylor
Testing & QA | 2024-09-01 | 2024-10-15 | 45 | Not Started | Sarah Lee
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | 15 | Planned | Chris White
Post-Deployment Review | 2024-11-01 | 2024-11-05 | 5 | Not Started | Team Lead