## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible
Project Planning | 2024-01-01 | 2024-01-15 | 15 | On Track | John Doe
Requirement Gathering | 2024-01-16 | 2024-02-05 | 21 | In Progress | Jane Smith
Design Phase | 2024-02-06 | 2024-03-15 | 41 | Planned | Mike Johnson
Development Phase | 2024-03-16 | 2024-05-31 | 76 | Not Started | Sarah Lee
Testing & QA | 2024-06-01 | 2024-07-15 | 45 | Planned | David Brown
Deployment & Go-Live | 2024-07-16 | 2024-07-31 | 16 | Not Started | Lisa Chen