## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | 100 | Sarah Johnson
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | 85 | Michael Lee
Design Phase | 2024-04-11 | 2024-05-15 | 45 | 60 | Anna Patel
Development Phase | 2024-05-16 | 2024-07-31 | 76 | 40 | David Kim
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | 75 | Linda Wang
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | 100 | James Taylor
Post-Implementation Review | 2024-09-16 | 2024-09-30 | 15 | 50 | Team Lead