## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Project Kickoff | 2024-03-01 | 2024-03-05 | 5 | Completed
Requirements Gathering | 2024-03-06 | 2024-03-18 | 13 | In Progress
Design Phase | 2024-03-19 | 2024-04-05 | 17 | Planned
Development | 2024-04-06 | 2024-05-15 | 40 | Not Started
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | Not Started
Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | Not Started