## Worksheet
Task | Start Date | End Date | Duration | Status | Progress (%)
Product Vision Finalization | 2024-03-15 | 2024-03-25 | 10 days | Completed | 100%
User Research & Feedback Collection | 2024-03-26 | 2024-04-10 | 15 days | In Progress | 65%
Prototype Design & Review | 2024-04-11 | 2024-04-25 | 15 days | Planned | 0%
UI/UX Development | 2024-04-26 | 2024-05-31 | 36 days | Not Started | 0%
Frontend Implementation | 2024-06-01 | 2024-07-15 | 65 days | Not Started | 0%
Backend Integration & API Setup | 2024-07-16 | 2024-08-31 | 66 days | Not Started | 0%
Testing & QA Cycle | 2024-09-01 | 2024-09-30 | 30 days | Not Started | 0%
Launch & Go-Live | 2024-10-01 | 2024-10-05 | 5 days | Not Started | 0%