## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Team | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Management Team | Completed | 100%
Market Research & Analysis | 2024-03-02 | 2024-03-15 | 14 | Strategy & Research Team | In Progress | 60%
Product Design Phase | 2024-03-16 | 2024-04-10 | 35 | Design Team | Not Started | 0%
Development Sprint 1 | 2024-04-11 | 2024-04-25 | 15 | Engineering Team | Not Started | 0%
User Testing & Feedback | 2024-04-26 | 2024-05-10 | 15 | QA & UX Team | Not Started | 0%
Final Review & Go-Live Planning | 2024-05-11 | 2024-05-15 | 5 | Project Management Team | Not Started | 0%