## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
Project Planning | 2024-03-01 | 2024-03-15 | 15 | Completed | 100%
Requirement Analysis | 2024-03-16 | 2024-04-10 | 35 | In Progress | 65%
Design Phase | 2024-04-11 | 2024-05-05 | 35 | Not Started | 0%
Development Phase | 2024-05-06 | 2024-07-15 | 71 | Not Started | 0%
Testing & QA | 2024-07-16 | 2024-08-31 | 46 | Not Started | 0%
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Not Started | 0%
Performance Tracking – Gantt Chart Template Version