## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Status | Responsible
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | 95% | Completed | John Doe
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 | 75% | In Progress | Jane Smith
Design Phase | 2024-02-16 | 2024-03-31 | 46 | 50% | Planned | Mike Johnson
Development Phase | 2024-04-01 | 2024-06-30 | 90 | 25% | Not Started | Sarah Lee
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | 45 | 0% | Not Started | David Brown
Go-Live & Deployment | 2024-08-16 | 2024-08-31 | 16 | 0% | Not Started | Lisa Wong