## Worksheet
Week | Task | Start Date | End Date | Duration (Days) | Status | Responsible Person
Week 1 | Project Kickoff Meeting | 2023-10-08 | 2023-10-10 | 3 | Completed | Alice Johnson
Week 2 | Requirements Gathering | 2023-10-11 | 2023-10-17 | 7 | In Progress | Bob Smith
Week 3 | Design Phase Initiation | 2023-10-18 | 2023-10-24 | 7 | Planned | Cara Lee
Week 4 | Prototype Development | 2023-10-25 | 2023-11-07 | 14 | Pending Approval | Dave Turner
Week 5 | Internal Testing | 2023-11-08 | 2023-11-14 | 7 | Not Started | Eve Martinez