## Worksheet
Performance Tracking – Team Use
Week | Objective | Progress (%) | Key Achievements | Risks/Challenges | Action Items
1 | Complete project kickoff and team alignment | 90% | Team meeting scheduled; goals defined | Limited bandwidth on day 1 | Finalize project timeline by Friday
2 | Develop initial product prototype | 75% | Prototype design approved by stakeholder | Feedback loop delays from client | Schedule client review in 48 hours
3 | Conduct user testing session | 60% | Identified 3 critical UX issues | Low participation from target group | Improve outreach strategy for next session
4 | Refine product based on feedback | 85% | UX improvements implemented; user satisfaction up by 20% | Design consistency issues across platforms | Standardize design language across all screens
5 | Prepare for beta launch | 100% | Beta users onboarded; feedback collection active | Technical bugs detected in mobile version | Fix critical bugs by launch date