## Worksheet
Date | Task | Assigned To | Status | Progress (%) | Notes
Mon, Apr 7 | Complete project proposal draft | John Doe | In Progress | 60% | Needs feedback from client team by end of week.
Tue, Apr 8 | Review design mockups | Jane Smith | Completed | 100% | Final approval received at 3 PM.
Wed, Apr 9 | Update project timeline | Mike Johnson | Pending | 0% | Waiting for stakeholder input.
Thu, Apr 10 | Hold team sync meeting | All Team | Completed | 100% | Agreed on next week’s deliverables.
Fri, Apr 11 | Prepare weekly performance report | Sarah Lee | In Progress | 40% | Final data collection pending.