## Worksheet
Date | Task/Activity | Assigned To | Status | Progress (%) | Notes
2024-04-01 | Product Roadmap Review | Jane Doe | Completed | 100% | Finalized Q3 roadmap with stakeholders.
2024-04-05 | UI/UX Prototype Design | John Smith | In Progress | 75% | Designs approved by product team; feedback pending.
2024-04-10 | Backend API Development | Michael Lee | Pending | 30% | Initial setup complete; integration testing scheduled.
2024-04-15 | Security Audit | Sarah Kim | Not Started | 0% | Preparation phase; tools and access secured.
2024-04-20 | Performance Testing | David Wong | Completed | 100% | All endpoints passed load tests; results documented.