## Worksheet
Team Member | Task Assigned | Target Date | Current Status | Progress % | Comments / Notes | Owner (Primary)
Alex Morgan | Develop UI Prototype | 2023-10-15 | In Progress | 60% | Needs feedback from design team by Oct 10. | Sarah Lee
Jordan Taylor | Conduct User Testing | 2023-10-20 | Pending Approval | 30% | Test participants not yet finalized. | Michael Chen
Nina Patel | Update Inventory System | 2023-10-25 | On Track | 100% | No notes. | Lena Ruiz
David Kim | Finalize Performance Metrics | 2023-10-30 | Delayed | 45% | Data sources not fully available. | Rachel Wong