## Worksheet
Date | Task | Assigned To | Start Time | End Time | Status | Progress (%) | Notes
01/04/2024 | Project Kickoff Meeting | John Smith | 09:00 AM | 11:00 AM | Completed | 100% | All stakeholders aligned on goals.
02/04/2024 | Requirements Gathering | Sarah Johnson | 10:00 AM | 12:30 PM | In Progress | 65% | Review with client ongoing.
03/04/2024 | Design Phase Review | Mike Chen | 14:00 PM | 16:30 PM | Pending | 30% | Final design feedback pending from team lead.
04/04/2024 | Development Start | Team A | 08:30 AM | 17:30 PM | Not Started | 0% | No codebase yet; waiting on approvals.