## Worksheet
Performance Tracking Planner – Startup Version
Week | Key Objective | Progress (%) | Actions Taken | Blockers & Risks | Owner
1 | Finalize product roadmap for Q1 | 60% | Mapped user personas, drafted features list | Unclear market demand – needs validation | Jane Doe
2 | Launch MVP with core features | 30% | Frontend development complete, backend in progress | Integration delays with payment gateway | <Mark Smith
3 | Begin user testing with 50 beta users | 0% | User sign-up flow tested internally | Limited access to early adopters | Sarah Lee
4 | Collect feedback and iterate on design | 50% | Conducted 3 focus groups, updated UI mockups | Time constraints in development team | Jane Doe
5 | Prepare go-to-market strategy | 20% | Competitor analysis completed | Limited brand awareness in target region | Mark Smith