## Worksheet
Week | Task | Assigned To | Start Date | Due Date | Status | Progress (%) | Notes
1 | Market Research Survey Design | Team A | 2024-04-01 | 2024-04-15 | On Track | 75% | Initial survey questions approved by Product Lead.
1 | Competitor Analysis Report | Team B | 2024-04-03 | 2024-04-20 | In Progress | 50% | Collecting data from 3 key competitors.
2 | User Persona Development | Team C | 2024-04-10 | 2024-04-30 | Pending | 15% | Waiting for feedback from UX team.
2 | Development Sprint Planning | All Teams | 2024-04-15 | 2024-04-30 | On Track | 90% | Agile sprint goals confirmed and shared.
3 | Final Prototype Review | Team A & B | 2024-05-01 | 2024-05-15 | Not Started | 0% | Prototype ready for review after QA.