## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Priority | Dependencies | Risk Level | Performance Metric
Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-03 | Completed | 100% | Low |  | None | Meeting attendance & alignment
Requirements Gathering | Sarah Lee | 2024-03-04 | 2024-03-15 | In Progress | 75% | Medium | Kickoff Meeting | Medium | Stakeholder feedback collected
Design Phase Finalization | Mike Chen | 2024-03-16 | 2024-03-31 | Planned | 0% | High | Requirements Finalized | High | Design approval from stakeholders
Development Sprint 1 | Team A | 2024-04-01 | 2024-04-15 | In Progress | 60% | Medium | Design Finalized | Medium | Code completion rate (daily)
QA Testing & Bug Fixing | Lisa Wong | 2024-04-16 | 2024-05-01 | Not Started | 0% | High | Development Sprint 1 Complete | High | Defect resolution rate (daily)
Deployment to Production | David Kim | 2024-05-02 | 2024-05-03 | Planned | 0% | Critical | QA Testing Complete | Critical | Uptime & response time after deployment
Total Tasks: |  |  |  |  | 6 | Performance Summary