## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Actual vs. Planned | Risk Level | Notes
P-001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | Completed | 100% | On Track | Low | All stakeholders confirmed.
P-002 | Requirements Gathering | John Smith | 2024-03-16 | 2024-04-10 | In Progress | 75% | On Track | Medium | Delays in stakeholder availability.
P-003 | UI/UX Design Finalization | Sarah Lee | 2024-04-11 | 2024-05-05 | Not Started | 0% | At Risk | High | Design review pending approval.
P-004 | Backend Development | Mike Johnson | 2024-05-06 | 2024-07-15 | Not Started | 0% | At Risk | High | Integration with third-party APIs delayed.
P-005 | Testing & Quality Assurance | Lisa Brown | 2024-07-16 | 2024-08-31 | Not Started | 0% | At Risk | High | Pending final development delivery.