## Worksheet
Task | Assigned To | Start Date | End Date | Status | Progress (%) | Notes
Project Kickoff Meeting | John Doe | 2024-03-15 | 2024-03-15 | Completed | 100% | All stakeholders were present and objectives agreed.
Requirement Gathering | Jane Smith | 2024-03-16 | 2024-03-31 | In Progress | 75% | Initial interviews completed; final documents due by end of month.
Design Phase | Mike Johnson | 2024-04-01 | 2024-04-15 | Not Started | 0% | Wireframes and UI mockups to be finalized.
Development | Team A | 2024-04-16 | 2024-05-31 | Not Started | 0% | Frontend and backend development to begin after design approval.
Testing & QA | Sarah Lee | 2024-06-01 | 2024-06-30 | Not Started | 0% | All modules to be tested for functionality and performance.
Deployment | Admin Team | 2024-07-01 | 2024-07-05 | Not Started | 0% | Production deployment after final testing.