## Worksheet
Project Name | Objective | Start Date | End Date th> | Current Status | Progress (%) | Owner | Key Milestones | Risk Level | Performance Score
Website Redesign | Improve user experience and mobile responsiveness | 2024-03-15 | 2024-06-30 | On Track | 75% | Sarah Johnson | Design Finalized, Content Approved, Launch Ready | Low | 8.5/10
Marketing Campaign 2024 | Increase brand awareness by 30% | 2024-04-01 | 2024-07-31 | On Track | 65% | David Kim | Ad Creative Review, Social Media Rollout | Medium | 7.2/10
Customer Onboarding System | Streamline new user registration and setup process | 2024-05-01 | 2024-08-15 | At Risk | 40% | Lisa Wong | Backend Development, UX Prototyping | High | 5.8/10
Performance Tracking Dashboard - Project Plan (Version 1.0)