## Worksheet
Project Name | Phase | Start Date | End Date | Responsible Person | Status | Performance Metric | Actual vs. Target | Remarks
Website Redesign Project | Discovery & Planning | 2024-03-01 | 2024-03-31 | Alice Johnson | On Track | User Survey Completion Rate | 95% vs 90% | Positive feedback on UX flow.
Mobile App Development | Development | 2024-04-01 | 2024-06-30 | Bob Smith | On Track | Daily Active Users (DAU) | 12,000 vs 15,000 | Beta testing completed with 92% satisfaction.
Customer Onboarding System | Implementation | 2024-05-01 | 2024-07-31 | Carol Davis | At Risk | Onboarding Completion Rate | 65% vs 85% | Delayed due to third-party API issues.