## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Priority | Dependencies | Resource Allocation | Risk Level | Actual vs. Budgeted Cost | Notes
P-001 | Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | Completed | 100% | High | None | Project Manager, Team Lead | Low | $0 / $5,000 | All stakeholders confirmed participation.
P-002 | Requirements Gathering | John Doe | 2024-03-16 | 2024-03-31 | In Progress | 75% | Medium | P-001 | Business Analyst, 2 Developers | Medium | $8,000 / $15,000 | Final requirements expected by March 31.
P-003 | System Design Phase | Lisa Chen | 2024-04-01 | 2024-04-15 | Not Started | 0% | High | P-002 | Lead Architect, 1 Designer | High | $0 / $12,000 | Design mockups and technical specifications.
P-004 | Development & Testing | Mike Brown | 2024-04-16 | 2024-05-31 | Planned | 0% | High | P-003 | Development Team (6) | Medium | $0 / $45,000 | Unit testing and integration testing to follow.
P-005 | User Acceptance Testing (UAT) | Sarah Lee | 2024-06-01 | 2024-06-15 | Not Started | 0% | High | P-004 | QA Team, End Users | High | $0 / $10,000 | Final validation with stakeholders.