## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | Finalized project scope and stakeholders.
Requirements Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | In Progress | 75% | User interviews completed; documentation in draft.
Design Phase | Alex Johnson | 2024-04-11 | 2024-05-05 | Not Started | 0% | Wireframes and UI mockups to be developed.
Development | Team A | 2024-05-06 | 2024-07-15 | Planned | 0% | Backend and frontend development scheduled.
Testing & Quality Assurance | Lisa Brown | 2024-07-16 | 2024-08-10 | Not Started | 0% | Functional and usability testing to begin.
Deployment | Mike Wilson | 2024-08-11 | 2024-08-15 | Not Started | 0% | Production deployment scheduled.
Post-Launch Review | Project Manager | 2024-08-16 | 2024-08-20 | Not Started | 0% | Evaluate performance and user feedback.