## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Priority | Resource Allocation | Milestone Reached? | Risk Level | Performance Notes
P001 | Project Initiation & Planning | John Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | High | Full Team (5) | Yes | Low | Planning approved; budget confirmed.
P002 | Market Research & Analysis | Jane Smith | 2024-03-16 | 2024-04-10 | In Progress | 75% | Medium | 3 Analysts | No | Medium | Data collection underway; sample size is 90% of target.
P003 | Product Design & Prototyping | Mike Johnson | 2024-04-11 | 2024-05-30 | Not Started | 0% | High | Design Team (6) | No | High | Risks related to timeline and design feasibility.
P004 | Development & Testing | Sarah Lee | 2024-06-01 | 2024-08-31 | Planned | 0% | Critical | Engineering Team (8) | No | Medium | Integration with legacy systems is a key concern.
P005 | User Training & Rollout | David Brown | 2024-09-01 | 2024-10-31 | Not Started | 0% | Medium | Training Staff (4) | No | Low | Final rollout schedule to be confirmed.