## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Kickoff Meeting | Alex Morgan | 2024-03-15 | 2024-03-15 | Completed | 100% | All stakeholders aligned on scope and deliverables.
Requirement Gathering | Sarah Lee | 2024-03-16 | 2024-03-28 | In Progress | 65% | Finalizing user stories and acceptance criteria.
UI/UX Design Phase | Jordan Kim | 2024-03-29 | 2024-04-15 | Not Started | 0% | Wireframes and mockups to be reviewed by stakeholders.
Development Phase | Team A | 2024-04-16 | 2024-05-31 | Not Started | 0% | Frontend and backend architecture in progress.
Testing & Quality Assurance | Mia Chen | 2024-06-01 | 2024-06-15 | Not Started | 0% | Unit, integration, and user acceptance testing.
Go-Live & Deployment | Tech Lead | 2024-06-16 | 2024-06-16 | Not Started | 0% | Deployment to production environment with backup plan.