## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Initiation | John Smith | 01/01/2024 | 01/15/2024 | Completed | 100% | All stakeholders on board. Baseline established.
Requirements Gathering | Jane Doe | 01/16/2024 | 02/14/2024 | In Progress | 75% | Finalizing user stories. Feedback from team in progress.
Design Phase | Alex Chen | 02/15/2024 | 03/10/2024 | Not Started | 0% | Wireframes and UI mockups to be developed.
Development | Team A | 03/11/2024 | 05/30/2024 | Not Started | 0% | Backend and frontend development schedule set.
Testing & QA | Lisa Wong | 06/01/2024 | 07/15/2024 | Not Started | 0% | Beta testing will begin after development.
Go-Live & Deployment | Mark Taylor | 07/16/2024 | 07/31/2024 | Not Started | 0% | Final deployment to production environment.