## Worksheet
Project Name | Team Member | Month | Key Objective | Progress (%) | Milestones Achieved | Issues & Risks | Next Steps | Owner
Product Launch Q3 | Sarah Johnson | September 2024 | Complete UI/UX design and final approval | 85% | Design finalized, UX reviewed by product lead | Final client feedback pending | Submit for final review in October | David Lee
Market Expansion | Michael Chen | September 2024 | Establish partnership with 3 new regional distributors | 40% | Signed initial agreement with Distributor A | Slow response from Distributor B; budget constraints | Negotiate revised terms and propose alternative partners | Michael Chen
Customer Support System Upgrade | Lisa Wong | September 2024 | Implement AI-powered chatbot for Tier 1 support | 60% | Chatbot prototype deployed in testing environment | Integration with CRM not fully stable | Finalize integration and conduct UAT by end of month | Lisa Wong