## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Kickoff Meeting | John Doe | 2024-03-01 | 2024-03-01 | Completed | 100% | All stakeholders aligned on goals.
Requirement Gathering | Jane Smith | 2024-03-02 | 2024-03-15 | In Progress | 65% | Client interviews completed; documentation in draft.
Design Phase | Mike Johnson | 2024-03-16 | 2024-04-10 | Not Started | 0% | Wireframes and mockups to be finalized.
Development | Sarah Lee | 2024-04-11 | 2024-06-30 | Not Started | 0% | Frontend and backend development scheduled.
Testing & QA | David Kim | 2024-07-01 | 2024-07-31 | Not Started | 0% | Bug tracking and user acceptance testing planned.
Deployment | Lisa Chen | 2024-08-01 | 2024-08-05 | Not Started | 0% | Go-live scheduled with monitoring setup.