## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Priority | Dependencies | Notes
P-001 | Project Kickoff Meeting | Alice Johnson | 2024-03-15 | 2024-03-15 | Completed | 100% | Low |  | All stakeholders aligned on goals.
P-002 | Requirements Gathering | Bob Smith | 2024-03-16 | 2024-04-10 | In Progress | 75% | Medium | P-001 | Finalizing user stories with stakeholders.
P-003 | Design Phase | Carol Davis | 2024-04-11 | 2024-05-05 | Not Started | 0% | High | P-002 | Wireframes and UI mockups to be developed.
P-004 | Development Phase | David Lee | 2024-05-06 | 2024-07-15 | Not Started | 0% | High | P-003 | Frontend and backend implementation.
P-005 | Testing & QA | Eva Martinez | 2024-07-16 | 2024-08-10 | Not Started | 0% | Medium | P-004 | Functional and performance testing.
P-006 | Deployment & Go-Live | Frank Wilson | 2024-08-11 | 2024-08-15 | Not Started | 0% | Low | P-005 | Production deployment and user training.