## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Remarks
Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-01 | Completed | 100% | All stakeholders aligned on goals and scope.
Requirements Gathering | Sarah Lee | 2024-03-02 | 2024-03-15 | In Progress | 65% | Finalizing user stories and acceptance criteria.
Design Phase | Mike Johnson | 2024-03-16 | 2024-03-31 | Pending Approval | 30% | Draft wireframes submitted for review.
Development Phase | Amy Chen | 2024-04-012024-05-31 | Not Started | 0% | Team awaiting design sign-off.
Testing & Quality Assurance | Dave Brown | 2024-06-01 | 2024-06-30 | Not Started | 0% | Scheduled after development completion.
Deployment & Go-Live | Lisa Wong | 2024-07-01 | 2024-07-15 | Not Started | 0% | Preliminary rollout plan in preparation.