## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Market Research | Sarah Johnson | 2024-03-15 | 2024-03-30 | Completed | 100% | Survey results compiled and analyzed.
Product Design | Mark Lee | 2024-04-01 | 2024-04-15 | In Progress | 65% | Wireframes finalized; user testing scheduled.
Development Phase | Team A | 2024-04-16 | 2024-05-31 | Not Started | 0% | Tech stack selected; planning in progress.
Marketing Launch | Lisa Chen | 2024-06-01 | 2024-06-15 | Planned | 0% | Campaign assets to be created.
Post-Launch Review | All Team Members | 2024-07-01 | 2024-07-10 | Not Started | 0% | Performance metrics to be collected and reviewed.