## Worksheet
Startup Project Plan – Performance Tracking
Project Name | Owner | Start Date | Target Milestone (Week) | KPIs & Metrics | Status | Action Items & Notes th>
Product MVP Launch | Jane Doe | 2024-03-01 | Week 8 | User engagement: ≥40%, Conversion rate: ≥15% | In Progress | Finalize user feedback loop by Week 7. Conduct A/B testing in Week 9.
Customer Onboarding Flow | John Smith | 2024-03-15 | Week 10 | Drop-off rate: ≤25%, NPS: ≥40 | In ReviewOptimize form fields; test with 50 beta users.
Revenue Growth Strategy | Lisa Chen | 2024-04-01 | Week 14 | MRR increase: +25%, Churn rate: ≤8% | Planned | Develop pricing tiers; schedule market validation meeting.
Team Productivity Metrics | Mike Rodriguez | 2024-03-05 | Ongoing (Bi-weekly) | Task completion rate: ≥90%, Cycle time: ≤7 days | On Track | No action required. Weekly stand-ups are effective.