## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Priority | Notes
Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | Completed | 100% | High | Finalized project scope and team roles.
Market Research Analysis | Alex Johnson | 2024-04-02 | 2024-04-15 | In Progress | 65% | Medium | Data collection underway; preliminary insights compiled.
UI/UX Design Phase | Sara Lee | 2024-04-16 | 2024-05-10 | Not Started | 0% | High | Wireframes and user flows to be developed.
Development Sprint 1 | Team Alpha | 2024-05-11 | 2024-06-05 | Not Started | 0% | High | Frontend and backend setup in progress.
Testing & QA Review | Mark Taylor | 2024-06-06 | 2024-06-30 | Not Started | 0% | Medium | All features to be tested for functionality and bugs.