## Worksheet
Week | Project Name | Objective | Key Activities | Progress (%) | Risks | Owner | Next Steps
Week 1 | Product Launch Phase | Finalize product design and user testing | Design review, prototype testing, feedback collection | 60% | Delayed prototyping due to vendor issues | John Smith | Resolve vendor delays and schedule revised testing
Week 2 | Marketing Strategy Development | Define target audience and campaign messaging | Audience research, messaging draft, stakeholder review | 75% | Low engagement from initial survey data | Sarah Lee | Refine audience segmentation and test new messaging
Week 3 | Development Sprint | Complete core feature development and QA testing | Feature implementation, bug fixing, internal QA | 45% | Critical bug in payment module | Mike Chen | Address payment module issues and retest functionality
Week 4 | Internal Review & Feedback Loop | Conduct stakeholder review and gather feedback | Presentation to leadership, user feedback session | 20% | Unclear goals in feedback summary | Emily Rodriguez | Clarify objectives and prepare structured feedback report