## Worksheet
Project Name | Team Member | Start Date | End Date | Performance Metric | Current Status | Progress (%) | Risk Level | Notes
Web Application Redesign | Alex Morgan | 2024-03-01 | 2024-06-30 | User Engagement Rate | On Track | 75% | Medium
Mobile App Development | Jordan Lee | 2024-04-15 | 2024-09-30 | App Load Time (ms) | At Risk | 45% | High | Backend delay affecting UI.
Marketing Campaign Launch | Taylor Reed | 2024-05-01 | 2024-07-31 | Conversion Rate | On Track | 85% | Low
Data Analytics Platform Upgrade | Sam Kim | 2024-03-10 | 2024-11-30 | Query Processing Speed | Delayed | 25% | High | Infrastructure migration issues.