## Worksheet
Project Name | Team Member | Task Assigned | Target Completion Date | Actual Completion Date | Status | Progress (%) | Remarks
Product Launch v2.0 | Alex Johnson | UI/UX Design Finalization | 2023-10-15 | 2023-10-14 | Completed | 100% | Design approved by stakeholders.
Customer Onboarding System | Sara Patel | Backend API Development | 2023-10-20 | 2023-10-18 | On Track | 85% | Minor performance tuning pending.
Marketing Campaign | David Kim | Content Strategy & Copywriting | 2023-10-25 | 2023-10-24 | Completed | 100% | Approved for distribution on 10/24.
Mobile App Optimization | Mia Chen | Performance Benchmarking | 2023-10-30 | - | In Progress | 45% | Waiting on device testing results.