## Worksheet
Performance Tracking – Project Template (Multi Page)
Performance Indicator | Target Value | Current Value | Status (Met / Below / Above) | Remarks | Last Updated
KPI: Project On-Time Delivery | 95% | 92% | Below | Late due to vendor delays | 2024-04-05
KPI: Budget Adherence | 100% | 98% | Met | No significant overruns | 2024-04-05
KPI: Team Productivity Rate | 85% | 87% | Above | Increased output due to process optimization | 2024-04-05
KPI: Client Satisfaction Score | 90% | 89% | Met | Slight dip in post-delivery feedback | 2024-04-05
KPI: Risk Mitigation Effectiveness | 100% | 96% | Below | Inadequate response to emerging risks | 2024-04-05
Performance Indicator | Target Value | Current Value | Status (Met / Below / Above) | Remarks | Last Updated
Milestone: Phase 1 Completion | Completed by 2024-03-30 | Completed on 2024-03-28 | Met | No deviations from plan | 2024-04-05
Milestone: Phase 2 Kickoff | Completed by 2024-04-15 | Pending | Below | Delayed due to resource allocation issues | 2024-04-05
Milestone: User Testing Completion | Completed by 2024-05-10 | Pending | Below | Testing schedule postponed | 2024-04-05
Milestone: Final Review & Approval | Completed by 2024-05-31 | Pending | Below | Approval process delayed due to stakeholder review cycle | 2024-04-05
Milestone: Go-Live Date | Completed by 2024-06-15 | Pending | Below | Revised to 2024-07-15 due to testing delays | 2024-04-05
Performance Indicator | Target Value | Current Value | Status (Met / Below / Above) | Remarks | Last Updated
Team Attendance Rate | 95% | 98% | Above | All team members present for key meetings | 2024-04-05
Employee Engagement Score (Monthly) | 80% | 78% | Below | Slight drop in survey scores due to workload pressure | 2024-04-05
Training Completion Rate | 100% | 95% | Below | 3 team members pending certification updates | 2024-04-05
Suggestion Implementation Rate | 85% | <89% | Above | High number of employee suggestions implemented this month | 2024-04-05
Conflict Resolution Time (Avg) | <7 days | 9 days | Below | Some escalated issues took longer than planned to resolve | 2024-04-05
Note: This template is designed for multi-page performance tracking in project management. Each table page represents a different dimension of performance (KPIs, milestones, team engagement).