## Worksheet
Task | Responsible | Start Date | End Date | Status | Progress (%) | Priority | Milestone?
Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | High | Yes
Requirements Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | In Progress | 75% | High | Yes
Design Phase | Mike Johnson | 2024-04-11 | 2024-05-05 | Not Started | 0% | Medium | Yes
Development | Team A | 2024-05-06 | 2024-07-15 | Not Started | 0% | High | No
Testing & QA | Lisa Brown | 2024-07-16 | 2024-08-10 | Not Started | 0% | High | Yes
Deployment | Admin Team | 2024-08-11 | 2024-08-15 | Not Started | 0% | Medium | Yes
Post-Implementation Review | Project Manager | 2024-08-16 | 2024-08-20 | Not Started | 0% | Low | Yes